## Sheet1
Inspection & Test Plan
Document No. KaFa 260312
Project: Ashburton Shed
Client: Terrace contracting
Date： 12th. Mar. 2026
Revision Records
Revision Number | Revison Description | Revised by | Date | Comments | Approved by | Date
A | Issued Rev A to address SGS's comment | Kafa | 2026-04-01
W = Witness Point ; M = Monitor ; P= Perform ; H = Hold Point.
No. | WORKS DESCRIPTION | QUALITY CONTROL ACTIVITY | ACCEPTANCE CRITERIA | Verifying Document | Stage/frequency | Inspection
[6 empty] | KaFa | SGS | Client
1 | Inspection & Testing
1.1 | Prepare Inspection and Test Plan | Review and Approval of Inspection and Test Plan | AS/NZS5131:2016, structure specification | Inspection and Test Plan Approved - Stamped/Signed | Prior to Works Execution | P | R | R
1.2 | Welding procedures | WPS/PQR/WPQ | AS/NZS5131:2016, AS/NZS 1554.1:2014, structure specification | WPS/PQR/WPQ | Prior to Works Execution | P | P/R | R
1.3 | Receipt and Issue of Construction Drawings | Draft Tekla model according to drawings of client | shop drawings | Acknowledge Receipt of Drawings from Client. Confirmed tekla model | Prior to Fabrication | P | R | R
1.4 | Quality plan/work method | Prepare project quality plan and work method statement | ISO9001 & AS/NZS3834 Structure Specification | Quality plan/work method | Under Ruly steel; Prior to Works Execution | P | R | R
1.5 | Sub-contrator control | inspeciton at Galvanizing factory | AS/NZS 4680:2025 AS/NZS 2312.2:2014 HDG600 | As per KaFa Inspection report | Each item | M/P | M | R
2 | Procurement
2.1 | Place Orders for Material | Review & Approval of Purchased Items | Structure Specification 3.3.2 AS/NZS 3678-350 AS/NZS 3679-300 AS/NZS 1163-350L0 or 450L0 | Purchase contract | All Purchase Orders | P | R | R
2.2 | Place Orders for Purchased Items | Review & Approval of Purchased Items | Conform to Drawing and Specification Requirements | Mill certificate | All Purchase Orders | P | R | R
3 | Manufacture
3.1 | Receipt of Fabrication Materials | Inspect Incoming Materials Document | Material & Mill Test Reports Confirm To Drawing Requirements. Heat/BatchNumber to be on all material | Raw material bills Incoming material inspection record | Each delivery Received - 100% of all heat numbers | P | R | R
3.2 | Raw material third party test | Tensile and chemical composition (C/Si/P/S/Mn) testing base on approved material types and Heat/Batch No. | Structure Specification 3.3.2 AS/NZS 3678-350 AS/NZS 3679-300 AS/NZS 1163-350L0 or 450L0 | Testing report | Each delivery Received - 100% of all heat numbers | P | P | R
3.5 | Materials cutting, shaping, holing and corners | Laser cutting | WMS AS/NZS5131:2016 Section 6 | shop drawings | All parts | P | M | R
3.6 | Dimensional Check Prior to Welding | Dimensional Check | shop drawings AS/NZS5131:2016 | Dimensions tolerance inspection report on Shop drawings | All parts | M/P | M | R
3.7 | Qualify Weld Procedures & Welding Consumables | PQR / WPS as per AS 1554.1:2004 | AS/NZS1554.1:2014 AS/NZS5131:2016 Section 7.4.1 Structure specification -Welding consumable nominal UTS≥480Mpa | Welding Procedure Register Welding Consumables Issue & Control Record |  | P | R | R
3.8 | Qualify Welders | WPQ as per AS 1554.1:2004 | AS/NZS1554.1:2014 ISO9606.1:2017 | See Welder Certificate | All welders | P | R | R
3.9 | Welding & Weld Repairs | 100% Weld& Weld Repair Inspection | AS\NZS 1554.1:2014 AS/NZS5131:2016 Approved WPS / shop drawings | Inspection record of weld | 100% | M/P | M | R
3.1 | Clean up & Spatter Removal onFabricated Components &Weldments | Final Visual Inspection of Weld Quality | AS\NZS 1554.1:2014 | Inspection record of weld | As per specification | W | M | R
3.11 | NDT Testing | 100% Visual Scanning all welds 100% Visual Examination for full penetration butt welds 25% Visual Examination for fillet welds, MT on welds with suspected lack of fusion or crack 10% MT all welds 25% UT for full penetration butt welds (2 of first 10 FPBW k-area 100% UT) | AS\NZS 1554.1:2014 | SGS NDT report | As per specification Increase testing to 100% until 3 consecutive components conform before reduce to the nominated frequency | P | P | R
4 | HDG
4.1 | Hot dip galvanized test | Galvanizing quality inspection and thickness testing | AS/NZS 4680:2025 | As per KaFa Inspection report | 100% | M/P | M | R
5 | Final Inspection
5.1 | Mark & Tag Ready for Packing &Transport | Mark as per item numbers | Loading list | As per KAFA package loading list | 100% | W/P | M | R
6 | Packing & Preparation For Shipment
6.1 | Packing Ready For Shipment | Standard packing as per plan | Packing Lists | Packing Lists | 100% | W/P
7 | Documentation
7.1 | Compile MDR |  |  |  |  | P | R | R
APPROVAL
Manufacturing: Name: Date: Signature: |  | Quality control: Name: Date: Signature: |  | Client: Name: Date: Signature:
Attchment List
1 | WPQ&PQR
2 | Quality Control System
3 | Project Processing Program
4 | Production Schedule